## Slide 1: MPD TPC Status (02.12.2022)
  TPC:
    vessel assembly, ROC chambers, gating grid system
  Sub-systems:
    Electronics
    LV+HV system (CAEN)
    Gas and cooling systems
    Laser calibration
  Integration TPC to MPD
    Electronics platform
    Cabling and piping
    Installation TPC to MPD
  Time schedule
Presented by S.Movchan

## Slide 2: MPD TPC main parameters
Item | Dimension
Length of the TPC | 340cm
Outer radius of vessel | 140cm
Inner radius of vessel | 27 cm
Outer radius of the drift volume | 133cm
Inner radius of the drift volume | 34cm
Length of the drift volume | 170cm (of each half)
HV electrode | Membrane at the center of the TPC
Electric field strength | ~140V/cm;
Magnetic field strength | 0.5 Tesla
Drift gas | 90% Ar+10% Methane, Atmospheric pres. + 2 mbar
Gas amplification factor | ~ 104
Drift velocity | 5.45 cm/µs;
Drift time | < 30µs;
Temperature stability | < 0.5°C
Number of readout chambers | 24 (12 per each end-plate)
Segmentation in φ | 30°
Pad size | 5x12mm2 and 5x18mm2
Number of pads | 95232
Pad raw numbers | 53
Pad numbers after zero suppression | < 10%
Maximal event rate | < 7 kHz ( Lum. 1027 )
Electronics shaping time | ~180 ns (FWHM)
Signal-to-noise ratio | 30:1
Signal dynamical range | 10 bits
Sampling rate | 10 MHz
Sampling depth | 310 time buckets

## Slide 3: TPC vessel assembly
  C1-C2 and C3-C4 cylinder – assembled
  TPC service wheels (2pc) - assembled
  HV membrane – tested
  TPC field cage assembly - Jan-Feb 2023
  TPC vessel ready – March 2023
TPC vessel assembly – in progress
ISO-6
Service wheel thermal panels (12pc)
Both service wheels - assembled
Rods (30 pc) - assembled
Bld. 217

## Slide 4: ROC chambers and gating grid system (GGS): status
24 pc serial ROCs – READY!
Test set up for ROC certification
Test set up for pads calibration
Leica MS60 - 1 second resolution
Leica AT960 +/-10 mkm +5 mkm/m
Leica AT403 +/-15 mkm +6 mkm/m
Scanner AS1+AT960 +/-50 mkm
+/- 30 mkm
Pad plane unflatness: example
Check pads geometry
systematic - up to 150 mkm
Full set of ROC alignment marks
Summary:
- measurements to do for all ROCs
- calibration of ROC marks and
3968 pads respect to ROC
“reference hole” - in progress
ROC gating grid system: test set up
Pulse rise time
- 500 ns, OK!
Mass-production – started
Delivery to JINR – Feb 2023
24 pc ROCs – tested

## Slide 5: TPC Sub-systems: electronics
Production version of the FE card:
DAQ prototype:
62 FE cards, RCU prototypes,
ROC, 2pc LVDBs, server interface
board - tests ongoing
Chart: TPC FE cards production status
| FECs manufactured | FECs to be manufactured in 2022 | FECs to be ordered
 | 467 | 260 | 761
N=727 pc
(48%)
11 ROCs chambers will be completed
at the end of 2022.
727 FECs of 1500 were produced.
Tests of the FEC basic functionality were shown the target characteristics (Noise and stability).
Testing of the readout system for one ROC is ongoing.
60 pc LVN9 were send back to Minsk:
- modification connection of power cables to LVN9 - in progress
- modification of LVN9 output voltages to FECs - in progress
- test of LVN9 with cooling radiator under full load (analog – 70 A, digital – 50 A) – in progress
LVN9 stabilizer
FE water cooling

## Slide 6: TPC Sub-systems: LV+HV (CAEN)
LV&HV system based on CAEN rad. hard design:
(up to 2000 Gauss and 15 kRad)
- power converters A3486 AC/DC (380 V -> 48 V) – 15+3 pc
- EASY3000 crates - 14+2 pc
- LV module - A3100B (8V/100A) - 48+8 pc
- LV module - A3100HBP (14V/50A) - 6 +2 pc
- HV modules –A3540P (+4kV/1mA) - 8+3 pc
- HV modules –A3540N (- 4kV/1mA) - 2+2 pc
Status:
LV+HV system: JINR-CAEN contract signed
Expected delivery date to JINR: August 2023
test system – tests ongoing
LV cables (halogen free, low smoke):
new cable S=50 mm2 – contract signed
delivery date to JINR - Feb 2023
HV cables - ordered

## Slide 7: TPC Sub-systems: gas and cooling
Gas supply
Racks
Tests - in progress
(H20 and Q2 sensors are replaced)
TPC volume
imitator
Full set – delivered
contract JINR-INP BSU (Minsk) – in progress
delivery – 30 September 2023
operation under manual control – during beam test 2024
fully automatic control – 30 September 2024
Gas system (Ar/CH4, 90:10)
Water cooling system
S=4x5 m2
h=2.5 m
MPD hall
S=1.2x3.6 m2
h=2.2 m
MPD

## Slide 8: TPC Sub-systems: laser calibration
Scheme for ½ TPC
Laser “planes” - 4
Micro-mirrors bundles per plane - 4
Beams from micro-mirrors bundle - 7
Laser “tracks” (N =112х2) - 224
micro-mirror
bundles
TPC
laser
laser
Laser beam monitor
Laser beam splitter

## Slide 9: NICA-MPD-Platform (NMP)
Common view
TPC + ECAL
cooling
Design and integration –
in progress …
TPC equipment

## Slide 10: MPD electronic platform
TPC equipment in racks on the 4th floor

## Slide 11
W side: cooling and gas pipes scheme
TPC cabling and piping
TPC list of cables and pipes

## Slide 12: TPC cabling and piping
Structures for
cables and pipes
fixation
Prototype for cabling and piping
Design - in progress
TPC+TOF+ECAL cabling – finished
Piping – not started yet
TPC
Beam pipe
Integration …

## Slide 13: Tooling for Installation TPC to MPD
24 tons,
max=0.41 mm
Bld. 217
Bld. 217 (MPD)
4 units for adjustment X, Y, Z
Design under discussions
Tooling manufacture –
Jan-July 2023
Delivery to JINR –
August 2023

## Slide 14: Time schedule and conclusion
Status:
  Integration TPC to MPD:
  TPC racks (8pc) - layout optimization in progress
  TPC rails (calculations, manufacture) - Feb 2023 –> June 2023 on critical path !!!
  rails installation to MPD - July 2023
  Tooling for installation TPC to MPD:
  design - under discussion
  tooling manufacture - Jan-July 2023 (7 month)
  delivery to JINR - August 2023
  TPC+ECAL cooling systems installation – up to Sept 30 2023
  TPC schedule:
  TPC installation to MPD Oct-Nov 2023
  cabling and piping Sept-Nov-Dec 2023
  MPD commissioning Jan-Feb 2024
Thank you !