## Лист1
Reduced sector Wheel
Quality and chronology sheet
Sector number, starts witn 0 | Approx. polishing date (Delivery number) | Status (Accepted/not specified/rejected) | Producer comment (MEPhI) | Recipient comment (JINR) | Geometry | <- I request Alexey Tishevsky to pick rather left or right, we are not sure which one is caller left or right
0 | 1 - 8 Apr 26 (1st) |  | Angle; Missaligment | Troubles with fiber+glue -> there is a angle on the final connector surface. Missaligment. SGF coupling troubles, Supports issue (including SGF damaging and the fact that connector is not seated properly on the tile row 5) | Left / Right
1 | 1 - 8 Apr 26 (1st) |  | Missaligment | Glue absent in several holes -> cludding RIP. Missaligment. SGF coupling troubles, Supports issue (including SGF damaging and the fact that connector is not seated properly on the tile row 5) | Left / Right
2 | 1 - 8 Apr 26 (1st) |  | Missaligment | Glue absent in several holes -> cludding RIP. Missaligment. SGF coupling troubles, Supports issue (including SGF damaging and the fact that connector is not seated properly on the tile row 5) | Left / Right
Secondary updates: better polishing quality, including higher effort and time-consumption.
3 | 13-15 Apr 26 (2nd, future) |  | Missaligment |  | Left / Right
4 | 13-15 Apr 26 (2nd, future) |  | Missaligment |  | Left / Right
5 | 13-15 Apr 26 (2nd, future) |  | No polish; Old connector, needs to be replaced via JINR Alexey Tishevsky |  | Left / Right
Now using 1.15 Diam connectors in order to achive alighment; What is more, new gluing technology (out and in) is used; Attempts on Supports removal are applied - trying to solve SGF trouples and Support issue. Slight update on connector model about so-called "раструб"
6 | 24-27 Apr 26 |  | Allighment! Out-and-in gluing technology -> damaged cladding (glue absence) |  | Left/Right
7 | 24-27 Apr 26 |  | Alighment! Back-gluing technology is applied (an old one) - less glue ansence - importante to check SGF coupling ability! The request - check for Supports issue, there should be none from now (in case of sec. 6-7 for sure, now we are paing special attention) |  | Left/Right